## KH Solar Plan (hidden)
FY 2024-25 ¦ Khavda Solar Projects Monthly Commissioning Plan (MWac) | [32 empty] | For Internal Purpose | [7 empty] | 2025-03-31
Priority | Project | SPV | Plot No | Plot No GP | Category | Category | MMS Type | Module Source | Module Wp | Capacity (MWac) | OL | Capacity (MWdc) |  | PSS No. | PSS Charging Date | SCOD | Commissioning as per Growth Plan | Plot Head | Commissioning as per Growth Plan (R5 - 08-Feb-25) | Capex BOQ Release Date | LTA Phase | Expected LTA Operationalization | Plant Code | SUPPLY Plant Code | SERVICE Plant Code | Commissioning as per Growth Plan | Charging Start | Charging Finish |  | Capex NFA Status | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total (MW)
10 | AGEL Merchant | ARE56L | S-08 |  | Merchant | Merchant | HSAT |  |  | 400 | 1.37 | 548 |  | PSS-09 | Charged |  |  | Arvind Kulshrestha | 2025-03-01 | [11 empty] | 2025-04-01: 150; 2025-05-01: 100 | 250
13 | AGEL Merchant | ARE56L | A-02 |  | Merchant | Merchant | HSAT |  |  | 225 | 1.37 | 308.25 |  | PSS-04 | Charged |  |  | Akhil Agarwal | 2025-03-01 | [11 empty] | 2025-04-01: 50 | 50
11 | MLP AP New | ARE57L | A-11 |  | PPA | PPA | HSAT |  |  | 500 | 1.36 | 680 |  | PSS-13 | Charged |  |  | Salim Beg | 2025-03-01 | [11 empty] | 2025-04-01: 187.5 | 187.5
12 | MLP AP New | ARE57L | A-12 |  | PPA | PPA | HSAT |  |  | 350 | 1.35 | 472.5 |  | PSS-13 | Charged |  |  | Bikash Kumar | 2025-03-01 | [11 empty] | 2025-06-01: 100; 2025-07-01: 250 | 350
14 | SECI H-3 | AHEJ5L | A-13 |  | PPA | PPA | FT |  |  | 570 | 1.4 | 798 |  | PSS-05 | Charged |  |  | Syed Ali | 2025-03-01 | [11 empty] | 2025-04-01: 295; 2025-06-01: 275 | 570
15 | AGEL Merchant | ARE45L | A-14 |  | Merchant | Merchant | HSAT |  |  | 250 | 1.37 | 342.5 |  | PSS-05 | Charged |  |  | Syed Ali | 2025-03-01 | [11 empty] | 2025-04-01: 150; 2025-05-01: 100 | 250
16 | MLP T3 AP | ARE56L | S-06 |  | PPA | PPA | HSAT |  |  | 500 | 1.37 | 685 |  | PSS-10 | Charged |  |  | Ramesh Suthar | 2025-03-01 | [11 empty] | 2025-04-01: 100; 2025-06-01: 100; 2025-07-01: 300 | 500
Monthwise FY 24-25 Projects (A) | [9 empty] | 4045 |  | 3834.25 | [18 empty] | 2025-04-01: 932.5; 2025-05-01: 200; 2025-06-01: 475; 2025-07-01: 550 | 2157.5
[31 empty] | 600 | 200 | 325 | 550
[15 empty] | Category |  | Category |  | Capacity (MWac) | Capacity (MWac) | [10 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[15 empty] | Merchant |  | Merchant |  | 550 | 1227 | [10 empty] | 350 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | PPA |  | PPA |  | 1607.5 | 1650 | [10 empty] | 582.5 | 0 | 475 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Group |  | Group |  | 0 | 150 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | EPC |  | EPC |  | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Total |  | Total |  | 2157.5 | 3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932.5 | 200 | 475 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[31 empty] | 1145 | 550 | 375
FY 2025-26 ¦ Khavda Solar Projects Monthly Commissioning Plan (MWac) | [30 empty] | 2025-06-01: In May-25 & Jun-25 @1.15 OL & balance 1.37 OL by Jul to Sep-25
Priority | Project | SPV | Plot No | Plot No GP | Category | Category | MMS Type | Module Source | Module Wp | Capacity (MWac) | OL | Capacity (MWdc) | IDT (No.s) | PSS No. | PSS Charging Date | SCOD | Commissioning as per Growth Plan | Plot Head | Commissioning as per Growth Plan (R5 - 08-Feb-25) | Capex BOQ Release Date | LTA Phase | Expected LTA Operationalization | Plant Code | SUPPLY Plant Code | SERVICE Plant Code | Commissioning as per Growth Plan | Charging Start | Charging Finish |  | Capex NFA Status | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
P-01 | Google Hybrid | ARE3L | A-6 | A18 | Merchant-Google | Merchant | HSAT | ALMM | 580 | 25 | 1.35 | 33.75 | 2 | PSS-08 | 2025-07-13 | - | 2025-06-30 | Trilochan Saggu | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-06-01: 25 | 25
P-02 | AGEL Merchant | ASEJ6PL | A-6 | A18, S9 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 35 | 1.35 | 47.25 | 3 | PSS-08 | 2025-07-13 | - | 2025-06-30 | Trilochan Saggu | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-06-01: 35 | 35
P-03 | AGEL Hybrid Merchant | ARE48L | S-8 | S7, S8 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 100 | 1.35 | 135 | 8 | PSS-09 | Charged | - | 2025-06-30 | Arvind / Dhritiman | 2025-06-30 | 2024-11-19 | Phase - III | 2025-12-31 | [8 empty] | 2026-01-01: 100 | 100
P-04 | AGEL Merchant | AHEJ5L | A-15a | A15 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | 12 | PSS-08 | 2025-07-13 | - | 2025-06-30 | Atul Kumar Kothari | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-11-01: 50; 2026-01-01: 100 | 150
P-05a | AGEL Hybrid Merchant | AGE26BL | S-5 | S5, S6 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 142 | 1.35 | 191.7 | 24 | PSS-10 | Charged | - | 2025-12-31 | P. Raja | 2025-06-30 | 2024-11-26 | Phase - III | 2025-12-31 | [8 empty] | 2025-05-01: 100; 2025-06-01: 42 | 142
P-05b | AGEL Merchant | AGE26BL | S-5 | S5, S6 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | 24 | PSS-10 | Charged | - | 2025-12-31 | P. Raja | 2025-06-30 | 2024-11-26 | Phase - III | 2025-12-31 | [8 empty] | 2025-06-01: 150 | 150
P-06 | AGEL Merchant | AGE24L | S-5 | S5, S6 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | 12 | PSS-10 | Charged | - | 2025-12-31 | P. Raja | 2025-06-30 | 2024-11-26 | Phase - III | 2025-12-31 | [8 empty] | 2025-05-01: 50; 2025-06-01: 100 | 150
P-07 | AGEL Merchant | AGE24L | A-14 | A13, A14, A17 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | 12 | PSS-05 | Charged | - |  | Syed Ali | 2025-06-30 | [11 empty] | 2025-11-01: 150 | 150
P-08 | Cement - Hybrid | ACL | A-1 | A1, A2 | Cement - Hybrid | Group | FT | ALMM | 580 | 125 | 1.36 | 170 | 10 | PSS-04 | Charged | - | 2025-06-30 | Rupesh Kumar | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-06-01: 125 | 125
P-14 | MLP T3 AP | AGE25CL | A-6 | A6 | PPA | PPA | HSAT | China |  | 75 | 1.35 | 101.25 | 6 | PSS-08 | 2025-07-13 | 2025-11-05 |  |  | 2025-10-01 | [11 empty] | 2025-11-01: 75 | 75
P-09 | MLP T1 J&K | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 50 | 1.36 | 68 | 4 | PSS-06 | 2025-11-15 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-09-01: 50 | 50
P-10 | MLP T1 CG | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 200 | 1.36 | 272 | 16 | PSS-06 | 2025-11-15 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-10-01: 200 | 200
P-11 | MLP T1 TN | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 167 | 1.36 | 227.12 | 14 | PSS-06 | 2025-11-15 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-10-01: 167 | 167
P-12 | MLP T1 OR | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 333 | 1.36 | 452.88 | 27 | PSS-06 | 2025-12-23 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-09-01: 333 | 333
P-13 | MLP T1 TR | AGE26AL | A10a | A9, A10 | PPA | PPA | FT | SEA |  | 50 | 1.36 | 68 | 4 | PSS-03 | Charged | 2024-09-26 | 2025-06-30 |  | 2025-09-30 | 2024-11-12 | Phase - II | 2025-03-31 | [8 empty] | 2025-09-01: 50 | 50
P-15 | MLP T3 AP | AGE25CL | A-6 | A6 | PPA | PPA | FT | China |  | 425 | 1.36 | 578 | 34 | PSS-08 | 0 | [15 empty] | 2025-12-01: 425 | 425
P-16 | AGEL Hybrid Merchant | AHEJ5L | S-4 | Merchant | Merchant | Merchant | HSAT |  |  | 300 | 1.35 | 405 | PSS-11 | [17 empty] | 2025-12-01: 100; 2026-01-01: 100; 2026-02-01: 100 | 300
P-17 | 0 | 0 | 0 | PPA | PPA | PPA | HSAT |  |  | 350 | 1.35 | 472.5 | 0 | [17 empty] | 2026-01-01: 150; 2026-02-01: 200 | 350
P-18a | KCTL | KCTL | A-15a | Group | Copper | Group | HSAT |  |  | 12.5 | 1.35 | 16.875 | PSS-08 | [29 empty] | 0
P-18b | MCIPL | MCIPL | A-15a | Group | Copper | Group | HSAT |  |  | 12.5 | 1.35 | 16.875 | PSS-08 | [29 empty] | 0
P-19 | AGEL Merchant | ASEJo6PL | A-15a | Merchant | Merchant | Merchant | HSAT |  |  | 25 | 1.35 | 33.75 | PSS-08 |  |  | 2025-11-05 |  |  | 2025-10-01 | [23 empty] | 0
Monthwise FY 25-26 Projects (B) | [9 empty] | 3027 |  | 4099.95 | [18 empty] | 0 | 150 | 477 | 0 | 0 | 433 | 367 | 275 | 525 | 450 | 300 | 0 | 2977
Monthwise FY 24-26 Projects (A) + (B) | [9 empty] | 7072 |  | 7934.2 | [18 empty] | 932.5 | 350 | 952 | 550 | 0 | 433 | 367 | 275 | 525 | 450 | 300 | 0 | 5134.5
FY Wise & Quaterly Breakup | [9 empty] | 7072 |  | 7934.2 | [18 empty] | 2025-04-01: 2234.5; 2025-07-01: 983; 2025-10-01: 1167; 2026-01-01: 750
5134.5
b. For 25-26 Merchant Projects 627 MW commissioning planned in May-25 & Jun-25 to be commissioned at 1.15 DC overloading, and full capacity DC overloading shall be achieved during July-25 to Sep-25 (need to be considered during revenue projections)
[15 empty] | Category |  | Category |  | Capacity (MWac) | Capacity (MWac) | [10 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[15 empty] | Merchant |  | Merchant |  | 1227 | 1227 | [10 empty] | 0 | 150 | 352 | 0 | 0 | 0 | 0 | 200 | 100 | 300 | 100 | 0 | 1202
[15 empty] | PPA |  | PPA |  | 1650 | 1650 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 433 | 367 | 75 | 425 | 150 | 200 | 0 | 1650
[15 empty] | Group |  | Group |  | 150 | 150 | [10 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125
[15 empty] | EPC |  | EPC |  | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Total |  | Total |  | 3027 | 3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 477 | 0 | 0 | 433 | 367 | 275 | 525 | 450 | 300 | 0
[31 empty] | 0 | 150 | 477 | 0 | 0 | 0 | 0 | 200 | 100 | 300 | 100 | 0
FY 2024-26 ¦ Khavda Solar Projects Monthly Commissioning Plan (MWac)
[15 empty] | Category |  | Category |  | Capacity (MWac) | Capacity (MWac) | [10 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[15 empty] | Merchant |  | Merchant |  | 1752 | 1227 | [10 empty] | 350 | 350 | 352 | 0 | 0 | 0 | 0 | 200 | 100 | 300 | 100 | 0
[15 empty] | PPA |  | PPA |  | 3257.5 | 1650 | [10 empty] | 582.5 | 0 | 475 | 550 | 0 | 433 | 367 | 75 | 425 | 150 | 200 | 0
[15 empty] | Group |  | Group |  | 125 | 150 | [10 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | EPC |  | EPC |  | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | Total |  | Total |  | 5134.5 | 3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932.5 | 350 | 952 | 550 | 0 | 433 | 367 | 275 | 525 | 450 | 300 | 0
[14 empty] | FY 24-25 Projects | [16 empty] | 932.5 | 200 | 475 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | Total FY 24-26 | [16 empty] | 932.5 | 350 | 952 | 550 | 0 | 433 | 367 | 275 | 525 | 450 | 300 | 0
[31 empty] | 932.5 |  | 1302 |  |  | 983
[14 empty] | 2775 | [16 empty] | 1820.3843 | 3879.1327 | 5479.9409 | 6247.1308 | 5643.9145 | 6566.6761 | 3374.6377 | 2741.8741 | 1475.6137 | 452.8851 | 165.2767 | 176.5385
[14 empty] | 1027 | [16 empty] | 2025-04-01: 4035; 2025-05-01: 1992; 2025-06-01: 1437
3995
[31 empty] | 5855.3843 | 5871.1327 | 6916.9409 | 6247.1308 | 5643.9145 | 6566.6761 | 3374.6377 | 2741.8741 | 1475.6137 | 452.8851 | 165.2767 | 176.5385
[31 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
[14 empty] | 1354385.6984 | [16 empty] | 175661.5298 | 176133.9807 | 207508.2271 | 187413.9244 | 169317.4342 | 197000.2844 | 101239.1318 | 82256.2234 | 44268.4102 | 13586.5525
3762.1825
[7 empty] | FT |  |  | 1350 | 325 | 1675
[7 empty] | HSAT |  |  | 1677 | 575 | 2252
[10 empty] | 3027 | 900 | 3927
|  |  | Plot No |  | Capacity (MWac)
A-1 |  |  | A-1 |  | 125 | [8 empty] | PSS-01 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-2 |  |  | A-2 |  | 0 | [8 empty] | PSS-02 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-6 |  |  | A-6 |  | 560 | [8 empty] | PSS-03 | 50 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
A10a |  |  | A10a |  | 50 | [8 empty] | PSS-04 | 125 | [15 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-12 |  |  | A-12 |  | 0 | [8 empty] | PSS-05 | 150 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0
A-13 |  |  | A-13 |  | 0 | [8 empty] | PSS-06 | 750 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 383 | 367 | 0 | 0 | 0 | 0 | 0
A-14 |  |  | A-14 |  | 150 | [8 empty] | PSS-07 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A-15a |  |  | A-15a |  | 200 | [8 empty] | PSS-08 | 710 | [15 empty] | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 125 | 425 | 100 | 0 | 0
A-16 |  |  | A-16 |  | 750 | [8 empty] | PSS-09 | 100 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0
S-2 |  |  | S-2 |  | 0 | [8 empty] | PSS-10 | 442 | [15 empty] | 0 | 150 | 292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S-4 |  |  | S-4 |  | 300 | [8 empty] | PSS-11 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S-5 |  |  | S-5 |  | 442 | [8 empty] | PSS-12 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S-6 |  |  | S-6 |  | 0 | [8 empty] | PSS-13 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S-8 |  |  | S-8 |  | 100 | [8 empty] | PSS-14 | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NHPC |  |  | NHPC |  | -1.5 | [8 empty] | NHPC | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total |  | 2675.5 | [8 empty] | Total | 2327 | 0
[31 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
[31 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FY 24-26
[6 empty] | Merchant | Merchant |  |  | 2102 | [20 empty] | 350 | 350 | 352 | 0 | 0 | 0 | 0 | 200 | 100 | 300 | 100 | 0 | 1752
[6 empty] | #REF! | PPA |  |  | 0 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Group | Group |  |  | 150 | [20 empty] | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125

## KH Solar Rephase (hidden)
FY 2024-25 ¦ Khavda Solar Projects Monthly Commissioning Plan (MWac) | [33 empty] | For Internal Purpose | [5 empty] | 2025-07-02
Priority | Project | SPV | Plot No | Plot No GP | Category | Category | MMS Type | Module Source | Module Wp | Capacity (MWac) | OL | Capacity (MWdc) | PSS No. | PSS Charging Date | SCOD | Commissioning as per Growth Plan | Plot Head | Commissioning as per Growth Plan (R5 - 08-Feb-25) | Capex BOQ Release Date | LTA Phase | Expected LTA Operationalization | Plant Code | SUPPLY Plant Code | SERVICE Plant Code | Commissioning as per Growth Plan | Charging Start | Charging Finish |  | Capex NFA Status | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total (MW)
10 | AGEL Merchant | ARE56L | S-08 |  | Merchant | Merchant | HSAT |  |  | 250 | 1.37 | 548 | PSS-09 | Charged |  |  | Arvind Kulshrestha | 2025-03-01 | [11 empty] | 2025-05-01: 75; 2025-06-01: 50; 2025-07-01: 50; 2025-08-01: 75; 2025-09-01: 0; 2025-10-01: 0 | 250
11 | MLP AP New | ARE57L | A-11 |  | PPA | PPA | HSAT |  |  | 50 | 1.36 | 680 | PSS-13 | Charged |  |  | Salim Beg | 2025-03-01 | [11 empty] | 2025-05-01: 50; 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0 | 50
12 | MLP AP New | ARE57L | A-12 |  | PPA | PPA | HSAT |  |  | 187.5 | 1.35 | 253.125 | PSS-13 | Charged |  |  | Bikash Kumar | 2025-03-01 | [11 empty] | 2025-04-01: 75; 2025-05-01: 112.5; 2025-06-01: 0; 2025-10-01: 0 | 187.5
13 | AGEL Merchant | ARE56L | A-02 |  | Merchant | Merchant | HSAT |  |  | 350 | 1.37 | 308.25 | PSS-04 | Charged |  |  | Akhil Agarwal | 2025-03-01 | [11 empty] | 2025-05-01: 50; 2025-06-01: 175; 2025-07-01: 0; 2025-08-01: 75; 2025-09-01: 50; 2025-10-01: 0 | 350
14 | SECI H-3 | AHEJ5L | A-13 |  | PPA | PPA | FT |  |  | 570 | 1.4 | 798 | PSS-05 | Charged |  |  | Syed Ali | 2025-03-01 | [11 empty] | 2025-04-01: 145; 2025-06-01: 150; 2025-07-01: 75; 2025-09-01: 50; 2025-10-01: 50; 2025-11-01: 100 | 570
15 | AGEL Merchant | ARE45L | A-14 |  | Merchant | Merchant | HSAT |  |  | 250 | 1.37 | 342.5 | PSS-05 | Charged |  |  | Syed Ali | 2025-03-01 | [11 empty] | 2025-04-01: 50; 2025-06-01: 125; 2025-08-01: 75; 2025-09-01: 0; 2025-10-01: 0 | 250
16 | MLP T3 AP | ARE56L | S-06 |  | PPA | PPA | HSAT |  |  | 500 | 1.37 | 685 | PSS-10 | Charged |  |  | Ramesh Suthar | 2025-03-01 | [11 empty] | 2025-04-01: 100; 2025-06-01: 137.5; 2025-07-01: 112.5; 2025-09-01: 50; 2025-10-01: 50; 2025-11-01: 50 | 500
Monthwise FY 24-25 Projects (A) | [9 empty] | 4045 |  | 3614.875 | [17 empty] | 370 | 287.5 | 637.5 | 237.5 | 225 | 150 | 100 | 150 |  |  |  |  | 2157.5
FY 2025-26 ¦ Khavda Solar Projects Monthly Commissioning Plan (MWac) | [29 empty] | 2025-06-01: In May-25 & Jun-25 @1.15 OL & balance 1.37 OL by Jul to Sep-25
Priority | Project | SPV | Plot No | Plot No GP | Category | Category | MMS Type | Module Source | Module Wp | Capacity (MWac) | OL | Capacity (MWdc) | PSS No. | PSS Charging Date | SCOD | Commissioning as per Growth Plan | Plot Head | Commissioning as per Growth Plan (R5 - 08-Feb-25) | Capex BOQ Release Date | LTA Phase | Expected LTA Operationalization | Plant Code | SUPPLY Plant Code | SERVICE Plant Code | Commissioning as per Growth Plan | Charging Start | Charging Finish |  | Capex NFA Status | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
P-01 | Google Hybrid | ARE3L | A-6 | A18 | Merchant-Google | Merchant | HSAT | ALMM | 580 | 25 | 1.35 | 33.75 | PSS-08 | 2025-04-20 | - | 2025-06-30 | Trilochan Saggu | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-07-01: 25; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0 | 25
P-02 | AGEL Merchant | ASEJ6PL | A-6 | A18, S9 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 35 | 1.35 | 47.25 | PSS-08 | 2025-04-20 | - | 2025-06-30 | Trilochan Saggu | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-07-01: 35; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2025-11-01: 0; 2025-12-01: 0 | 35
P-03 | AGEL Hybrid Merchant | ARE48L | S-8 | S7, S8 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 100 | 1.35 | 135 | PSS-09 | Charged | - | 2025-06-30 | Arvind / Dhritiman | 2025-06-30 | 2024-11-19 | Phase - III | 2025-12-31 | [8 empty] | 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 50; 2025-09-01: 0; 2025-11-01: 50; 2025-12-01: 0 | 100
P-04 | AGEL Merchant | AHEJ5L | A-15a | A15 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | PSS-08 | 2025-04-20 | - | 2025-06-30 | Atul Kumar Kothari | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [10 empty] | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 50 |  |  | 150
P-05 | AGEL Hybrid Merchant | AGE26BL | S-5 | S5, S6 | Merchant-Hybrid | Merchant | HSAT | ALMM | 580 | 142 | 1.35 | 191.7 | PSS-10 | Charged | - | 2025-12-31 | P. Raja | 2025-06-30 | 2024-11-26 | Phase - III | 2025-12-31 | [8 empty] | 2025-07-01: 50; 2025-08-01: 0; 2025-09-01: 75; 2025-10-01: 17 | 142
P-05 | AGEL Merchant | AGE26BL | S-5 | S5, S6 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | PSS-10 | 0 | - | 2025-12-31 | P. Raja | 2025-06-30 | 2024-11-26 | Phase - III | 2025-12-31 | [8 empty] | 2025-10-01: 45; 2025-11-01: 105 | 150
P-06 | AGEL Merchant | AGE24L | S-5 | S5, S6 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | PSS-10 | Charged | - | 2025-12-31 | P. Raja | 2025-06-30 | 2024-11-26 | Phase - III | 2025-12-31 | [10 empty] | 0 | 0 | 0 | 0 | 0 |  | 0 | 50 | 100 |  | 150
P-07 | AGEL Merchant | AGE24L | A-14 | A13, A14, A17 | Merchant | Merchant | HSAT | ALMM | 580 | 150 | 1.35 | 202.5 | PSS-05 | Charged | - |  | Syed Ali | 2025-06-30 | [11 empty] | 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 0; 2025-09-01: 0; 2025-10-01: 0; 2026-01-01: 50; 2026-02-01: 100 | 150
P-08 | Cement - Hybrid | ACL | A-1 | A1, A2 | Cement - Hybrid | Group | FT | ALMM | 580 | 125 | 1.36 | 170 | PSS-04 | Charged | - | 2025-06-30 | Rupesh Kumar | 2025-06-30 | 2024-11-19 | Phase - II | 2025-03-31 | [8 empty] | 2025-06-01: 0; 2025-07-01: 0; 2025-08-01: 75; 2025-10-01: 50; 2025-11-01: 0; 2025-12-01: 0 | 125
P-14 | MLP T3 AP | AGE25CL | A-6 | A6 | PPA | PPA | HSAT | China |  | 75 | 1.35 | 101.25 | PSS-08 | 2025-04-20 | 2025-11-05 |  |  | 2025-10-01 | [11 empty] | 2025-08-01: 75 | 75
P-09 | MLP T1 J&K | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 50 | 1.36 | 68 | PSS-06 | 2025-07-10 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-12-01: 50; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0 | 50
P-10 | MLP T1 CG | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 200 | 1.36 | 272 | PSS-06 | 2025-07-10 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-12-01: 50; 2026-01-01: 100; 2026-02-01: 50; 2026-03-01: 0 | 200
P-11 | MLP T1 TN | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 167 | 1.36 | 227.12 | PSS-06 | 2025-07-10 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2025-12-01: 50; 2026-01-01: 117; 2026-02-01: 0; 2026-03-01: 0 | 167
P-12 | MLP T1 OR | AGE26AL | A-16 | A16 | PPA | PPA | FT | SEA |  | 333 | 1.36 | 452.88 | PSS-06 | 2025-07-10 | 2025-03-18 | 2025-09-30 |  | 2025-09-30 | 2024-11-12 | Phase - I | 2024-01-18 | [8 empty] | 2026-01-01: 100; 2026-02-01: 100; 2026-03-01: 133 | 333
P-13 | MLP T1 TR | AGE26AL | A10a | A9, A10 | PPA | PPA | FT | SEA |  | 50 | 1.36 | 68 | PSS-03 | Charged | 2024-09-26 | 2025-06-30 |  | 2025-09-30 | 2024-11-12 | Phase - II | 2025-03-31 | [8 empty] | 2025-09-01: 50 | 50
P-15 | MLP T3 AP | AGE25CL | A-6 | A6 | PPA | PPA | FT | China |  | 425 | 1.36 | 578 | PSS-08 | Charged | 2025-11-05 |  |  | 2025-10-01 | [11 empty] | 2026-01-01: 150; 2026-02-01: 150; 2026-03-01: 125 | 425
P-16 | AGEL Hybrid Merchant | AHEJ5L | S-4 | Merchant | Merchant | Merchant | HSAT |  |  | 300 | 1.35 | 405 | PSS-11 | [16 empty] | 2025-12-01: 100; 2026-01-01: 100; 2026-02-01: 100 | 300
P-17 | MLP AP New | ARE57L | A-11 | PPA | PPA | PPA | HSAT |  |  | 350 | 1.35 | 472.5 | PSS-13 | [16 empty] | 2025-12-01: 150; 2026-01-01: 200 | 350
P-18a | KCTL | KCTL | A-15a | Group | Copper | Group | HSAT |  |  | 12.5 | 1.35 | 16.875 | PSS-08 | [16 empty] | 2026-02-01: 12.5 | 12.5
P-18b | MCIPL | MCIPL | A-15a | Group | Copper | Group | HSAT |  |  | 12.5 | 1.35 | 16.875 | PSS-08 | [16 empty] | 2026-02-01: 12.5 | 12.5
P-19 | AGEL Merchant | ASEJo6PL | A-15a | Merchant | Merchant | Merchant | HSAT |  |  | 25 | 1.35 | 33.75 | PSS-08 | [16 empty] | 2026-02-01: 25 | 25
Monthwise FY 25-26 Projects (B) | [9 empty] | 3027 | 28.42 | 4099.95 | 0 |  | 320429 | 596814 | 0 | 734054 | 592981 | 0 | 594059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 200 | 125 | 162 | 205 | 400 | 917 | 650 | 258 | 3027
Monthwise FY 24-26 Projects (A) + (B) | [9 empty] | 7072 |  | 7714.825 | [17 empty] | 370 | 287.5 | 637.5 | 347.5 | 425 | 275 | 262 | 355 | 400 | 917 | 650 | 258
FY Wise & Quaterly Breakup | [9 empty] | 7072 |  | 7714.825 | [17 empty] | 2025-04-01: 1295; 2025-07-01: 1047.5; 2025-10-01: 1017; 2026-01-01: 1825
5184.5
b. For 25-26 Merchant Projects 627 MW commissioning planned in May-25 & Jun-25 to be commissioned at 1.15 DC overloading, and full capacity DC overloading shall be achieved during July-25 to Sep-25 (need to be considered during revenue projections)

## Summary Linked
8 | AGEL FY 25-26 Commissioning Status Update | [8 empty] | For Chairman Budget Purpose @6.5GW +535 MW carryover | [11 empty] | 2025-12-31
3 | [8 empty] | Monthwise Distribution | [13 empty] | Quarterly Distribution
[8 empty] | Plan / Actual | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total Capacity | Cumm till 30-Nov-25 | Q1 | Q2 | Q3 | Q4
| AGEL Overall FY 2025-26 (1+2) | [6 empty] | Plan | 1114.5 | 532 | 1546.4 | 643.6 | 26 | 459 | 419 | 655 | 1039 | 562.4 | 0 | 75.9 | 7072.8 | 5395.5 | 3192.9 | 1128.6 | 2113 | 638.3
[8 empty] | PPA | 582.5 | 0 | 475 | 622.8 | 26 | 459 | 419 | 351 | 909 | 300 | 0 | 0 | 4144.3 | 2935.3 | 1057.5 | 1107.8 | 1679 | 300
[8 empty] | Merchant | 506 | 500.8 | 646.4 | 20.8 | 0 | 0 | 0 | 304 | 130 | 262.4 | 0 | 75.9 | 2446.3 | 1978 | 1653.2 | 20.8 | 434 | 338.3
[8 empty] | Group | 26 | 31.2 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 482.2 | 482.2 | 482.2 | 0 | 0 | 0
[8 empty] | Rephase | 474 | 313.5 | 848.7 | 575.5 | 653 | 353 | 366 | 459 | 782.8 | 971 | 880 | 396.3 | 7072.8 | 4042.7 | 1636.2 | 1581.5 | 1607.8 | 2247.3
[8 empty] | PPA | 320 | 162.5 | 462.5 | 187.5 | 150 | 200 | 100 | 254 | 782.8 | 717 | 550 | 258 | 4144.3 | 1836.5 | 945 | 537.5 | 1136.8 | 1525
[8 empty] | Merchant | 154 | 125 | 355 | 238 | 278 | 153 | 216 | 205 | 0 | 254 | 330 | 138.3 | 2446.3 | 1724 | 634 | 669 | 421 | 722.3
[8 empty] | Group | 0 | 26 | 31.2 | 150 | 225 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 482.2 | 482.2 | 57.2 | 375 | 50 | 0
[8 empty] | Actual / Fcst | 474 | 313.5 | 848.7 | 127.6 | 537.3 | 531.2 | 203 | 333.2 | 482.2 | 951.9 | 876.1 | 910.1 | 6588.8 | 3368.5 | 1636.2 | 1196.1 | 1018.4 | 2738.1
[8 empty] | PPA | 320 | 162.5 | 462.5 | 0 | 137.5 | 175 | 203 | 246.8 | 207.2 | 575 | 425 | 745.8 | 3660.3 | 1707.3 | 945 | 312.5 | 657 | 1745.8
[8 empty] | Merchant | 154 | 125 | 355 | 127.6 | 249.8 | 306.2 | 0 | 86.4 | 50 | 376.9 | 451.1 | 164.3 | 2446.3 | 1404 | 634 | 683.6 | 136.4 | 992.3
[8 empty] | Group | 0 | 26 | 31.2 | 0 | 150 | 50 | 0 | 0 | 225 | 0 | 0 | 0 | 482.2 | 257.2 | 57.2 | 200 | 225 | 0
[8 empty] | Plan / Actual | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total Capacity | Cumm till 30-Nov-25 | Q1 | Q2 | Q3 | Q4
| 1. AGEL Overall Solar FY 2025-26 (A + B + C) | [6 empty] | Plan | 932.5 | 350 | 1302 | 550 | 0 | 433 | 367 | 525 | 909 | 500 | 0 | 0 | 5868.5 | 4459.5 | 2584.5 | 983 | 1801 | 500
[8 empty] | PPA | 582.5 | 0 | 475 | 550 | 0 | 433 | 367 | 325 | 909 | 300 | 0 | 0 | 3941.5 | 2732.5 | 1057.5 | 983 | 1601 | 300
[8 empty] | Merchant | 350 | 350 | 402 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 1502 | 1302 | 1102 | 0 | 200 | 200
[8 empty] | Group | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 425 | 425 | 0 | 0 | 0
[8 empty] | Rephase | 370 | 287.5 | 687.5 | 497.5 | 575 | 275 | 262 | 355 | 684 | 867 | 750 | 258 | 5868.5 | 3309.5 | 1345 | 1347.5 | 1301 | 1875
[8 empty] | PPA | 320 | 162.5 | 462.5 | 187.5 | 150 | 200 | 100 | 150 | 684 | 717 | 550 | 258 | 3941.5 | 1732.5 | 945 | 537.5 | 934 | 1525
[8 empty] | Merchant | 50 | 125 | 225 | 160 | 200 | 75 | 112 | 205 | 0 | 150 | 200 | 0 | 1502 | 1152 | 400 | 435 | 317 | 350
[8 empty] | Group | 0 | 0 | 0 | 150 | 225 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 425 | 425 | 0 | 375 | 50 | 0
[8 empty] | Actual / Fcst | 370 | 287.5 | 687.5 | 60 | 412.5 | 500 | 125 | 250 | 425 | 837.5 | 704.5 | 725 | 5384.5 | 2692.5 | 1345 | 972.5 | 800 | 2267
[8 empty] | PPA | 320 | 162.5 | 462.5 | 0 | 137.5 | 175 | 125 | 200 | 150 | 575 | 425 | 725 | 3457.5 | 1582.5 | 945 | 312.5 | 475 | 1725
[8 empty] | Merchant | 50 | 125 | 225 | 60 | 125 | 275 | 0 | 50 | 50 | 262.5 | 279.5 | 0 | 1502 | 910 | 400 | 460 | 100 | 542
[8 empty] | Group | 0 | 0 | 0 | 0 | 150 | 50 | 0 | 0 | 225 | 0 | 0 | 0 | 425 | 200 | 0 | 200 | 225 | 0
| S. No. | Project Name | SPV | Type | Plot / Location / PSS | Capacity | Type | Plan Actual | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total Capacity | Cumm till 30-Nov-25 | Q1 | Q2 | Q3 | Q4
A. Khavda Solar Projects
| 1 | AGEL Merchant | ARE56L | Merchant | S-08 | 250 | Merchant | Plan | 150 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 75 | 50 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 125 | 125 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 75 | 50 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 125 | 125 | 0 | 0
| 2 | AGEL Merchant | ARE56L | Merchant | A-02 | 50 | Merchant | Plan | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
| 2 | AGEL Merchant | ARE56L | Merchant | A-02 |  | Merchant | Rephase | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
| 2 | AGEL Merchant | ARE56L | Merchant | A-02 |  | Merchant | Actual / Fcst | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
| 3 | MLP AP New | ARE57L | PPA | A-11 | 187.5 | PPA | Plan | 187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.5 | 187.5 | 187.5 | 0 | 0 | 0
| 3 | MLP AP New | ARE57L | PPA | A-11 |  | PPA | Rephase | 75 | 112.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.5 | 187.5 | 187.5 | 0 | 0 | 0
| 3 | MLP AP New | ARE57L | PPA | A-11 |  | PPA | Actual / Fcst | 75 | 112.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 187.5 | 187.5 | 187.5 | 0 | 0 | 0
| 4 | MLP AP New | ARE57L | PPA | A-12 | 350 | PPA | Plan | 0 | 0 | 100 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 100 | 250 | 0 | 0
| 4 | MLP AP New | ARE57L | PPA | A-12 |  | PPA | Rephase | 0 | 50 | 175 | 0 | 75 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 350 | 225 | 125 | 0 | 0
| 4 | MLP AP New | ARE57L | PPA | A-12 |  | PPA | Actual / Fcst | 0 | 50 | 175 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 350 | 350 | 225 | 0 | 125 | 0
| 5 | SECI H-3 | AHEJ5L | PPA | A-13 | 570 | PPA | Plan | 295 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 570 | 570 | 570 | 0 | 0 | 0
| 5 | SECI H-3 | AHEJ5L | PPA | A-13 |  | PPA | Rephase | 145 | 0 | 150 | 75 | 0 | 50 | 50 | 100 | 0 | 0 | 0 | 0 | 570 | 570 | 295 | 125 | 150 | 0
| 5 | SECI H-3 | AHEJ5L | PPA | A-13 |  | PPA | Actual / Fcst | 145 | 0 | 150 | 0 | 50 | 75 | 75 | 0 | 75 | 0 | 0 | 0 | 570 | 495 | 295 | 125 | 150 | 0
| 6 | AGEL Merchant | ARE45L | Merchant | A-14 | 250 | Merchant | Plan | 150 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 250 | 0 | 0 | 0
| 6 | AGEL Merchant | ARE45L | Merchant | A-14 |  | Merchant | Rephase | 50 | 0 | 125 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 175 | 75 | 0 | 0
| 6 | AGEL Merchant | ARE45L | Merchant | A-14 |  | Merchant | Actual / Fcst | 50 | 0 | 125 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 175 | 75 | 0 | 0
| 7 | MLP T3 AP | ARE56L | PPA | S-06 | 500 | PPA | Plan | 100 | 0 | 100 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 500 | 200 | 300 | 0 | 0
| 7 | MLP T3 AP | ARE56L | PPA | S-06 |  | PPA | Rephase | 100 | 0 | 137.5 | 112.5 | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 500 | 500 | 237.5 | 162.5 | 100 | 0
| 7 | MLP T3 AP | ARE56L | PPA | S-06 |  | PPA | Actual / Fcst | 100 | 0 | 137.5 | 0 | 87.5 | 100 | 0 | 75 | 0 | 0 | 0 | 0 | 500 | 500 | 237.5 | 187.5 | 75 | 0
| 8 | Google Hybrid | ARE3L | Merchant | A-6 | 25 | Merchant | Plan | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 25 | 0 | 0 | 0
| 8 | Google Hybrid | ARE3L | Merchant | A-6 |  | Merchant | Rephase | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 25 | 0 | 0
| 8 | Google Hybrid | ARE3L | Merchant | A-6 |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 25 | 0 | 0
| 9 | AGEL Merchant | ASEJ6PL | Merchant | A-6 | 35 | Merchant | Plan | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 35 | 0 | 0 | 0
| 9 | AGEL Merchant | ASEJ6PL | Merchant | A-6 |  | Merchant | Rephase | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 35 | 0 | 0
| 9 | AGEL Merchant | ASEJ6PL | Merchant | A-6 |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 0 | 35 | 0 | 0
| 10 | AGEL Hybrid Merchant | AGE25BL | Merchant | S-8 | 100 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 100
| 10 | AGEL Hybrid Merchant | AGE25BL | Merchant | S-8 |  | Merchant | Rephase | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 50 | 50 | 0
| 10 | AGEL Hybrid Merchant | AGE25BL | Merchant | S-8 |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 100 | 0 | 0
| 11 | AGEL Merchant | AHEJ5L | Merchant | A-15a | 150 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 100 | 0 | 0 | 150 | 50 | 0 | 0 | 50 | 100
| 11 | AGEL Merchant | AHEJ5L | Merchant | A-15a |  | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 50 | 0 | 0 | 150 | 100 | 0 | 0 | 100 | 50
| 11 | AGEL Merchant | AHEJ5L | Merchant | A-15a |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 50 | 0 | 150 | 50 | 0 | 50 | 0 | 100
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 | 292 | Merchant | Plan | 0 | 100 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 292 | 292 | 292 | 0 | 0 | 0
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 |  | Merchant | Rephase | 0 | 0 | 0 | 50 | 0 | 75 | 62 | 105 | 0 | 0 | 0 | 0 | 292 | 292 | 0 | 125 | 167 | 0
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 75 | 67 | 0 | 292 | 100 | 0 | 50 | 100 | 142
| 12a | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 | 142 |  |  | 0 | 100 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 | 142 | 142 | 0 | 0 | 0
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 |  |  |  | 0 | 0 | 0 | 50 | 0 | 75 | 17 | 0 | 0 | 0 | 0 | 0 | 142 | 142 | 0 | 125 | 17 | 0
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 42 | 0 | 142 | 100 | 0 | 50 | 50 | 42
| 12b | AGEL Merchant | AGE26BL | Merchant | S-5 | 150 |  |  | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 150 | 0 | 0 | 0
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 105 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 150 | 0
| 12 | AGEL Hybrid Merchant | AGE26BL | Merchant | S-5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 75 | 25 | 0 | 150 | 0 | 0 | 0 | 50 | 100
| 13 | AGEL Merchant | AGE24L | Merchant | S-5 | 150 | Merchant | Plan | 0 | 50 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 150 | 0 | 0 | 0
| 13 | AGEL Merchant | AGE24L | Merchant | S-5 |  | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 0 | 150 | 0 | 0 | 0 | 0 | 150
| 13 | AGEL Merchant | AGE24L | Merchant | S-5 |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.5 | 87.5 | 0 | 150 | 0 | 0 | 0 | 0 | 150
| 14 | AGEL Merchant | AGE24L | Merchant | A-14 | 150 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 150 | 0
| 14 | AGEL Merchant | AGE24L | Merchant | A-14 |  | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 0 | 150 | 0 | 0 | 0 | 0 | 150
| 14 | AGEL Merchant | AGE24L | Merchant | A-14 |  | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 150 | 0 | 0 | 0 | 0 | 150
| 15 | Cement - Hybrid | ACL | Group | A-1 | 125 | Group | Plan | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 125 | 0 | 0 | 0
| 15 | Cement - Hybrid | ACL | Group | A-1 |  | Group | Rephase | 0 | 0 | 0 | 0 | 75 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 75 | 50 | 0
| 15 | Cement - Hybrid | ACL | Group | A-1 |  | Group | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 75 | 0 | 0 | 0 | 125 | 50 | 0 | 50 | 75 | 0
| 16 | MLP T3 AP | AGE25CL | PPA | A-6 | 75 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 0 | 75 | 0
| 16 | MLP T3 AP | AGE25CL | PPA | A-6 |  | PPA | Rephase | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 0 | 75 | 0 | 0
| 16 | MLP T3 AP | AGE25CL | PPA | A-6 |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 75 | 0
| 17 | MLP T1 J&K | AGE26AL | PPA | A-16 | 50 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 50 | 0 | 0
| 17 | MLP T1 J&K | AGE26AL | PPA | A-16 |  | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 50 | 0
| 17 | MLP T1 J&K | AGE26AL | PPA | A-16 |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 50
| 18 | MLP T1 CG | AGE26AL | PPA | A-16 | 200 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0 | 0 | 200 | 0
| 18 | MLP T1 CG | AGE26AL | PPA | A-16 |  | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 50 | 0 | 200 | 0 | 0 | 0 | 50 | 150
| 18 | MLP T1 CG | AGE26AL | PPA | A-16 |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175 | 25 | 0 | 200 | 0 | 0 | 0 | 0 | 200
| 19 | MLP T1 TN | AGE26AL | PPA | A-16 | 167 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 167 | 167 | 0 | 0 | 167 | 0
| 19 | MLP T1 TN | AGE26AL | PPA | A-16 |  | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 117 | 0 | 0 | 167 | 0 | 0 | 0 | 50 | 117
| 19 | MLP T1 TN | AGE26AL | PPA | A-16 |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 67 | 0 | 167 | 0 | 0 | 0 | 0 | 167
| 20 | MLP T1 OR | AGE26AL | PPA | A-16 | 333 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 333 | 0 | 333 | 0 | 0
| 20 | MLP T1 OR | AGE26AL | PPA | A-16 |  | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 133 | 333 | 0 | 0 | 0 | 0 | 333
| 20 | MLP T1 OR | AGE26AL | PPA | A-16 |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 183 | 0 | 333 | 0 | 0 | 0 | 0 | 333
| 21 | MLP T1 TR | AGE26AL | PPA | A10a | 50 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 50 | 0 | 0
| 21 | MLP T1 TR | AGE26AL | PPA | A10a |  | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 50 | 0 | 0
| 21 | MLP T1 TR | AGE26AL | PPA | A10a |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 0 | 0 | 50 | 0
| 22 | MLP T3 AP | AGE25CL | PPA | A-6 | 425 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 425 | 0
| 22 | MLP T3 AP | AGE25CL | PPA | A-6 |  | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 125 | 425 | 0 | 0 | 0 | 0 | 425
| 22 | MLP T3 AP | AGE25CL | PPA | A-6 |  | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 150 | 175 | 425 | 0 | 0 | 0 | 0 | 425
| A. Subtotal (Khavda Solar Projects) |  |  |  |  | 4484.5 |  | Plan | 932.5 | 350 | 952 | 550 | 0 | 433 | 367 | 275 | 425 | 200 | 0 | 0 | 4484.5 | 3859.5 | 2234.5 | 983 | 1067 | 200
[8 empty] | PPA | 582.5 | 0 | 475 | 550 | 0 | 433 | 367 | 75 | 425 | 0 | 0 | 0 | 2907.5 | 2482.5 | 1057.5 | 983 | 867 | 0
[8 empty] | Merchant | 350 | 350 | 352 | 0 | 0 | 0 | 0 | 200 | 0 | 200 | 0 | 0 | 1452 | 1252 | 1052 | 0 | 200 | 200
[8 empty] | Group | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 125 | 0 | 0 | 0
[8 empty] | Rephase | 370 | 287.5 | 637.5 | 347.5 | 425 | 275 | 262 | 355 | 150 | 617 | 500 | 258 | 4484.5 | 2959.5 | 1295 | 1047.5 | 767 | 1375
[8 empty] | PPA | 320 | 162.5 | 462.5 | 187.5 | 150 | 200 | 100 | 150 | 150 | 467 | 300 | 258 | 2907.5 | 1732.5 | 945 | 537.5 | 400 | 1025
[8 empty] | Merchant | 50 | 125 | 175 | 160 | 200 | 75 | 112 | 205 | 0 | 150 | 200 | 0 | 1452 | 1102 | 350 | 435 | 317 | 350
[8 empty] | Group | 0 | 0 | 0 | 0 | 75 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 125 | 125 | 0 | 75 | 50 | 0
[8 empty] | Actual / Fcst | 370 | 287.5 | 637.5 | 60 | 262.5 | 500 | 125 | 250 | 275 | 837.5 | 704.5 | 175 | 4484.5 | 2492.5 | 1295 | 822.5 | 650 | 1717
[8 empty] | PPA | 320 | 162.5 | 462.5 | 0 | 137.5 | 175 | 125 | 200 | 150 | 575 | 425 | 175 | 2907.5 | 1582.5 | 945 | 312.5 | 475 | 1175
[8 empty] | Merchant | 50 | 125 | 175 | 60 | 125 | 275 | 0 | 50 | 50 | 262.5 | 279.5 | 0 | 1452 | 860 | 350 | 460 | 100 | 542
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 75 | 0 | 0 | 0 | 125 | 50 | 0 | 50 | 75 | 0
B. Rajasthan Solar Projects
| 1 | Cement RJ | ACL | Group | Essel park | 300 | Group | Plan | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0
[7 empty] | Group | Rephase | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 300 | 0 | 0
[7 empty] | Group | Actual / Fcst | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 300 | 150 | 0 | 150 | 150 | 0
| 2 | Merchant | ASEJ6PL | Merchant | Bap | 50 | Merchant | Plan | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
| 3 | MLP AP New | AGE26BL | PPA | Bandha | 534 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 284 | 0 | 0 | 0 | 534 | 250 | 0 | 0 | 534 | 0
[7 empty] | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 0 | 0 | 0 | 534 | 0 | 0 | 0 | 534 | 0
[7 empty] | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | MLP T1 | AGE25BL | PPA | Bandha | 500 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 300 | 0 | 0 | 500 | 0 | 0 | 0 | 200 | 300
[7 empty] | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 500 | 0 | 0 | 0 | 0 | 500
[7 empty] | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 250
| B. Rajasthan Solar Projects |  |  |  |  | 1384 |  | Plan | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 250 | 484 | 300 | 0 | 0 | 1384 | 600 | 350 | 0 | 734 | 300
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 484 | 300 | 0 | 0 | 1034 | 250 | 0 | 0 | 734 | 300
[8 empty] | Merchant | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 300 | 0 | 0 | 0
[8 empty] | Rephase | 0 | 0 | 50 | 150 | 150 | 0 | 0 | 0 | 534 | 250 | 250 | 0 | 1384 | 350 | 50 | 300 | 534 | 500
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 534 | 250 | 250 | 0 | 1034 | 0 | 0 | 0 | 534 | 500
[8 empty] | Merchant | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 300 | 0 | 0
[8 empty] | Actual / Fcst | 0 | 0 | 50 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 250 | 600 | 200 | 50 | 150 | 150 | 250
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 250 | 0 | 0 | 0 | 0 | 250
[8 empty] | Merchant | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 300 | 150 | 0 | 150 | 150 | 0
C. Rajasthan Solar Projects (Additional to Chairman Plan - 500 MW)
| 3 | NHPC BOO | ASEB1PL | PPA | Baiya | 600 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 300
| C. Rajasthan Solar Projects (Additional to Chairman Plan - 500 MW) |  |  |  |  | 600 |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 300
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 0 | 0 | 0 | 0 | 300
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D1. Khavda Solar (Copper + Merchant - 50 MW)
| 25 | KCTL | KCTL | Group | A-15a | 12.5 | Group | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Group | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 12.5 | 0 | 0 | 0 | 0 | 12.5
[7 empty] | Group | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 12.5 | 0 | 0 | 0 | 0 | 12.5
| 26 | MCIPL | MCIPL | Group | A-15a | 12.5 | Group | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Group | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 12.5 | 0 | 0 | 0 | 0 | 12.5
[7 empty] | Group | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.5 | 0 | 12.5 | 0 | 0 | 0 | 0 | 12.5
| 27 | AGEL Merchant | ASEJo6PL | Merchant | A-15a | 25 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 25
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 25
| D1. Khavda Solar (Copper + Merchant - 50 MW) |  |  |  |  | 50 |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 50
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 25
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 25
[8 empty] | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 50
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 25
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 25
D2. Khavda Solar (Additional for Internal - 650 MW)
| 23 | AGEL Hybrid Merchant | AHEJ5L | Merchant | S-4 | 300 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 200 | 0 | 350 | 0 | 0 | 0 | 0 | 350
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 300 | 0 | 0 | 0 | 100 | 200
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 24 | MLP AP New | ARE57L | PPA | A-12 | 350 | PPA | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 300 | 0 | 0 | 0 | 100 | 200
[7 empty] | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 200 | 0 | 0 | 350 | 0 | 0 | 0 | 150 | 200
[7 empty] | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| D2. Khavda Solar (Additional from Internal - 650 MW) |  |  |  |  | 650 |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 250 | 300 | 0 | 650 | 0 | 0 | 0 | 100 | 550
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 300 | 0 | 0 | 0 | 100 | 200
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 200 | 0 | 350 | 0 | 0 | 0 | 0 | 350
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 300 | 100 | 0 | 650 | 0 | 0 | 0 | 250 | 400
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 200 | 0 | 0 | 350 | 0 | 0 | 0 | 150 | 200
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 0 | 300 | 0 | 0 | 0 | 100 | 200
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Plan / Actual | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Total Capacity | Cumm till 30-Nov-25 | Q1 | Q2 | Q3 | Q4
| 2. AGEL Overall Wind FY 2025-26 (A + C) | [6 empty] | Plan | 182 | 182 | 244.4 | 93.6 | 26 | 26 | 52 | 130 | 130 | 62.4 | 0 | 75.9 | 1204.3 | 936 | 608.4 | 145.6 | 312 | 138.3
[8 empty] | PPA | 0 | 0 | 0 | 72.8 | 26 | 26 | 52 | 26 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 0 | 124.8 | 78 | 0
[8 empty] | Merchant | 156 | 150.8 | 244.4 | 20.8 | 0 | 0 | 0 | 104 | 130 | 62.4 | 0 | 75.9 | 944.3 | 676 | 551.2 | 20.8 | 234 | 138.3
[8 empty] | Group | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
[8 empty] | Rephase | 104 | 26 | 161.2 | 78 | 78 | 78 | 104 | 104 | 98.8 | 104 | 130 | 138.3 | 1204.3 | 733.2 | 291.2 | 234 | 306.8 | 372.3
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 98.8 | 0 | 0 | 0 | 202.8 | 104 | 0 | 0 | 202.8 | 0
[8 empty] | Merchant | 104 | 0 | 130 | 78 | 78 | 78 | 104 | 0 | 0 | 104 | 130 | 138.3 | 944.3 | 572 | 234 | 234 | 104 | 372.3
[8 empty] | Group | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
[8 empty] | Actual / Fcst | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 83.2 | 57.2 | 114.4 | 171.6 | 185.1 | 1204.3 | 676 | 291.2 | 223.6 | 218.4 | 471.1
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 46.8 | 57.2 | 0 | 0 | 20.8 | 202.8 | 124.8 | 0 | 0 | 182 | 20.8
[8 empty] | Merchant | 104 | 0 | 130 | 67.6 | 124.8 | 31.2 | 0 | 36.4 | 0 | 114.4 | 171.6 | 164.3 | 944.3 | 494 | 234 | 223.6 | 36.4 | 450.3
[8 empty] | Group | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
A. Khavda Wind Projects
| 1 | AGEL Merchant | AGE24L | Merchant | PSS-04 | 52 | Merchant | Plan | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 0 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 52 | 52 | 0 | 0 | 0
| 2 | Hybrid Cement | ACL | Group | PSS-04 | 57.2 | Group | Plan | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
[7 empty] | Group | Rephase | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
[7 empty] | Group | Actual / Fcst | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
| 3 | AGEL Merchant | AHEJ5L | Merchant | PSS-04 | 62.4 | Merchant | Plan | 52 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.4 | 62.4 | 62.4 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 52 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.4 | 62.4 | 62.4 | 0 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 52 | 0 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.4 | 62.4 | 62.4 | 0 | 0 | 0
| 4 | AGEL Hybrid Merchant | AGE26BL | Merchant | PSS-10 | 156 | Merchant | Plan | 52 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 156 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 119.6 | 26 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 119.6 | 36.4 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 119.6 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 156 | 145.6 | 119.6 | 26 | 0 | 10.4
| 5 | AGEL Merchant | AHEJ5L | Merchant | PSS-08 | 67.6 | Merchant | Plan | 0 | 0 | 67.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67.6 | 67.6 | 67.6 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 52 | 15.6 | 0 | 0 | 0 | 0 | 0 | 67.6 | 67.6 | 0 | 52 | 15.6 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 31.2 | 0 | 31.2 | 0 | 5.2 | 0 | 0 | 67.6 | 62.4 | 0 | 31.2 | 31.2 | 5.2
| 6 | AGEL Merchant | ARE41L | Merchant | PSS-08 | 130 | Merchant | Plan | 0 | 36.4 | 93.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 130 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 52 | 26 | 26 | 26 | 0 | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 104 | 26 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 124.8 | 0 | 0 | 5.2 | 0 | 0 | 0 | 0 | 130 | 130 | 0 | 124.8 | 5.2 | 0
| 7 | Google Hybrid | ARE3L | Merchant | PSS-08 | 15.6 | Merchant | Plan | 0 |  | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6 | 15.6 | 15.6 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6 | 15.6 | 0 | 15.6 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 15.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.6 | 15.6 | 0 | 15.6 | 0 | 0
| 8 | Google Hybrid | ARE3L | Merchant | PSS-08 | 26 | Merchant | Plan | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 26 | 0 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 26 | 0 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 0 | 26 | 0 | 0
| 9 | AGEL Hybrid Merchant | ASEJ6PL | Merchant | PSS-08 | 62.4 | Merchant | Plan | 0 | 0 | 41.6 | 20.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62.4 | 62.4 | 41.6 | 20.8 | 0 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 62.4 | 0 | 0 | 0 | 0 | 0 | 62.4 | 62.4 | 0 | 0 | 62.4 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31.2 | 20.8 | 10.4 | 62.4 | 0 | 0 | 0 | 0 | 62.4
| 10 | SECI H-3 | AHEJ5L | PPA | PSS-05 | 202.8 | PPA | Plan | 0 | 0 | 0 | 72.8 | 26 | 26 | 52 | 26 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 0 | 124.8 | 78 | 0
[7 empty] | PPA | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 98.8 | 0 | 0 | 0 | 202.8 | 104 | 0 | 0 | 202.8 | 0
[7 empty] | PPA | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 46.8 | 57.2 | 0 | 0 | 20.8 | 202.8 | 124.8 | 0 | 0 | 182 | 20.8
| 11a | AGEL Merchant | AGE25CL | Merchant | PSS-11 | 156 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 52 | 0 | 0 | 0 | 156 | 104 | 0 | 0 | 156 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 52 | 0 | 156 | 0 | 0 | 0 | 0 | 156
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 62.4 | 15.6 | 156 | 0 | 0 | 0 | 0 | 156
| 12a | AGEL Merchant | AGE26AL | Merchant | PSS-12 | 140.4 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 62.4 | 0 | 0 | 140.4 | 0 | 0 | 0 | 78 | 62.4
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 62.4 | 140.4 | 0 | 0 | 0 | 0 | 140.4
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 62.4 | 140.4 | 0 | 0 | 0 | 0 | 140.4
| A. Subtotal (Khavda Wind Projects) |  |  |  |  | 1128.4 |  | Plan | 182 | 182 | 244.4 | 93.6 | 26 | 26 | 52 | 130 | 130 | 62.4 | 0 | 0 | 1128.4 | 936 | 608.4 | 145.6 | 312 | 62.4
[8 empty] | PPA | 0 | 0 | 0 | 72.8 | 26 | 26 | 52 | 26 | 0 | 0 | 0 | 0 | 202.8 | 202.8 | 0 | 124.8 | 78 | 0
[8 empty] | Merchant | 156 | 150.8 | 244.4 | 20.8 | 0 | 0 | 0 | 104 | 130 | 62.4 | 0 | 0 | 868.4 | 676 | 551.2 | 20.8 | 234 | 62.4
[8 empty] | Group | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
[8 empty] | Rephase | 104 | 26 | 161.2 | 78 | 78 | 78 | 104 | 104 | 98.8 | 104 | 130 | 62.4 | 1128.4 | 733.2 | 291.2 | 234 | 306.8 | 296.4
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104 | 98.8 | 0 | 0 | 0 | 202.8 | 104 | 0 | 0 | 202.8 | 0
[8 empty] | Merchant | 104 | 0 | 130 | 78 | 78 | 78 | 104 | 0 | 0 | 104 | 130 | 62.4 | 868.4 | 572 | 234 | 234 | 104 | 296.4
[8 empty] | Group | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
[8 empty] | Actual / Fcst | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 83.2 | 57.2 | 114.4 | 171.6 | 109.2 | 1128.4 | 676 | 291.2 | 223.6 | 218.4 | 395.2
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 46.8 | 57.2 | 0 | 0 | 20.8 | 202.8 | 124.8 | 0 | 0 | 182 | 20.8
[8 empty] | Merchant | 104 | 0 | 130 | 67.6 | 124.8 | 31.2 | 0 | 36.4 | 0 | 114.4 | 171.6 | 88.4 | 868.4 | 494 | 234 | 223.6 | 36.4 | 374.4
[8 empty] | Group | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 57.2 | 57.2 | 0 | 0 | 0
B. Khavda Wind (Additional for Internal - 421 MW)
| 11b | AGEL Merchant | AGE25CL | Merchant | PSS-11(32.2 MW) PSS-14(67.6 MW) | 98.8 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.8 | 0 | 0 | 98.8 | 0 | 0 | 0 | 0 | 98.8
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.8 | 0 | 0 | 98.8 | 0 | 0 | 0 | 0 | 98.8
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 15.6 | 72.8 | 98.8 | 0 | 0 | 0 | 0 | 98.8
| 12b | AGEL Merchant | AGE26AL | Merchant | PSS-14 | 312 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6 | 156 | 114.4 | 312 | 0 | 0 | 0 | 0 | 312
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41.6 | 156 | 114.4 | 312 | 0 | 0 | 0 | 0 | 312
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.4 | 135.2 | 140.4 | 312 | 0 | 0 | 0 | 0 | 312
| 13 | AGEL Merchant | AGE25BL | Merchant | PSS-09 | 10.4 | Merchant | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 0 | 0 | 10.4 | 0 | 0 | 0 | 10.4 | 0
[7 empty] | Merchant | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 0 | 0 | 10.4 | 0 | 0 | 0 | 10.4 | 0
[7 empty] | Merchant | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 0 | 0 | 10.4 | 0 | 0 | 0 | 0 | 10.4
| B. Subtotal (Additional for Internal - 421 MW) |  |  |  |  | 421.2 |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 140.4 | 156 | 114.4 | 421.2 | 0 | 0 | 0 | 10.4 | 410.8
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 140.4 | 156 | 114.4 | 421.2 | 0 | 0 | 0 | 10.4 | 410.8
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 140.4 | 156 | 114.4 | 421.2 | 0 | 0 | 0 | 10.4 | 410.8
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 140.4 | 156 | 114.4 | 421.2 | 0 | 0 | 0 | 10.4 | 410.8
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 150.8 | 213.2 | 421.2 | 0 | 0 | 0 | 0 | 421.2
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 150.8 | 213.2 | 421.2 | 0 | 0 | 0 | 0 | 421.2
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C. Mundra Wind - 76 MW (Chairman)
| 1 | Merchant-Wind | AWEK3L | Merchant | Mundra North | 75.9 | Merchant | Plan | 2026-03-01: 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[7 empty] | Merchant | Rephase | 2026-03-01: 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[7 empty] | Merchant | Actual / Fcst | 2026-03-01: 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
| C. Mundra Wind |  |  |  |  | 75.9 |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Rephase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Actual / Fcst | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[8 empty] | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Merchant | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.9 | 75.9 | 0 | 0 | 0 | 0 | 75.9
[8 empty] | Group | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D. Mundra Wind - (Additional for Internal 224.4)
| 1 | Merchant-Wind | AWEK3L | Merchant | Mundra North | 247.5 | Merchant | Plan | 2026-01-01: 115.5; 2026-02-01: 115.5; 2026-03-01: 16.5 | 247.5 | 0 | 0 | 0 | 0 | 247.5
[7 empty] | Merchant | Rephase | 2026-01-01: 66; 2026-02-01: 56.1; 2026-03-01: 0 | 122.1 | 0 | 0 | 0 | 0 | 122.1
[7 empty] | Merchant | Actual / Fcst | 2026-02-01: 52.8; 2026-03-01: 194.7 | 247.5 | 0 | 0 | 0 | 0 | 247.5
Khavda Projects
[9 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[8 empty] | Plan | 1114.5 | 532 | 1196.4 | 643.6 | 26 | 459 | 419 | 405 | 555 | 262.4
[8 empty] | Rephase | 474 | 313.5 | 798.7 | 425.5 | 503 | 353 | 366.5 | 458.5 | 248.8 | 721 | 630 | 320.4
[8 empty] | Actual / Fcst | 474 | 313.5 | 798.7 | 127.6 | 387.3 | 531.2 | 203 | 370 | 818 | 972 | 388 | 267
OS Khavda Projects
[9 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[8 empty] | Plan | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 250 | 484 | 300 | 0 | 75.9
[8 empty] | Rephase | 0 | 0 | 50 | 150 | 150 | 0 | 0 | 0 | 534 | 250 | 250 | 75.9
[8 empty] | Actual / Fcst | 0 | 0 | 50 | 0 | 150 | 0 | 150 | 0 | 0 | 200 | 150 | 759.9
[11 empty] | 50 |  | 150 |  | 150 |  |  | 200 | 150 | 684

## KH Wind Actual
Out of 57.2 MW (11 WTGs), 7 WTG TR Done in Nov-25, but COD in Dec-25
[7 empty] | Forecast | Actual
FY 2025-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) | [16 empty] | Date: 30-Dec-25
Sl. | Project | SPV | Category | Capacity (MW) | WTG Nos. | PSS No. | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
1 | AGEL Merchant (Wind) | AGE24L | Merchant | 52 | 10 | PSS-04 | 52
2 | Hybrid Cement (Wind) | ACL | Group | 57.2 | 11 | PSS-04 |  | 26 | 31.2
3 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 62.4 | 12 | PSS-04 | 52 |  | 10.4
4 | AGEL Hybrid Merchant (Wind) | AGE26BL | Merchant | 156 | 30 | PSS-10 |  |  | 119.6 | 26 | [6 empty] | 10.4
5 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 67.6 | 13 | PSS-08 | [5 empty] | 31.2 |  | 31.2 |  | 5.2
6 | AGEL Merchant (Wind) | ARE41L | Merchant | 130 | 25 | PSS-08 |  |  |  |  | 124.8 |  |  | 5.2
7 | Google Hybrid (Wind) | ARE3L | Merchant | 15.6 | 3 | PSS-08 |  |  |  | 15.6
8 | Google Hybrid (Wind) | ARE3L | Merchant | 26 | 5 | PSS-08 |  |  |  | 26
9 | AGEL Hybrid Merchant (Wind) | ASEJ6PL | Merchant | 62.4 | 12 | PSS-08 | [9 empty] | 31.2 | 20.8 | 10.4
10 | SECI H-3 (Wind) | AHEJ5L | PPA | 202.8 | 39 | PSS-05 | [6 empty] | 78 | 46.8 | 57.2 |  |  | 20.8
11a | AGEL Merchant (Wind) | AGE25CL | Merchant | 156 | 30 | PSS-11 | [9 empty] | 78 | 62.4 | 15.6
12a | AGEL Merchant (Wind) | AGE26AL | Merchant | 140.4 | 27 | PSS-12 | [10 empty] | 78 | 62.4
| Total - MW |  |  | 1128.4 |  |  | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 83.2 | 57.2 | 114.4 | 171.6 | 109.2
[7 empty] | 291.2 |  |  | 223.6 |  |  | 218.4 |  |  | 395.2
| Total - WTG |  |  |  | 217 |  | 20 | 5 | 31 | 13 | 24 | 6 | 15 | 16 | 11 | 22 | 33 | 21
[7 empty] | 56 |  |  | 43 |  |  | 42 |  |  | 76
Additional for internal
11b | AGEL Merchant (Wind) | AGE25CL | Merchant | 98.8 | 19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 15.6 | 72.8
|  |  |  | 31.2 | 6 | PSS-11 | [9 empty] | 10.4 | 15.6 | 5.2
|  |  |  | 67.6 | 13 | PSS-14 | [11 empty] | 67.6
12b | AGEL Merchant (Wind) | AGE26AL | Merchant | 312 | 60 | PSS-14 | [9 empty] | 36.4 | 135.2 | 140.4
13 | AGEL Merchant | AGE25BL | Merchant | 10.4 | 2 | PSS-09 | [9 empty] | 10.4
| Total (for Internal) |  |  | 520 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57.2 | 150.8 | 213.2
| Total - MW |  |  | 1648.4 | 81 | 0 | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 83.2 | 57.2 | 171.6 | 322.4 | 322.4
[8 empty] | Mwac | WTG
[7 empty] | Budget Plan | 1128 | 217
[7 empty] | Internal Plan | 1549.6 | 298
[7 empty] | Actual YTD Dec-25 | 733.2 | 141
[7 empty] | Balance Budget | 394.8 | 76
[7 empty] | Balance Internal | 816.4 | 157

## KH Solar Actual
Phase-III: Khavda Solar Projects Monthly COD Actuals & Forecast (MWac) | [15 empty] | TR Done in Nov-25 but COD in Dec-25 | [7 empty] | 2025-12-30 |  |  | In addition to COD |  |  | Physical Progress Status till 27/28-Dec |  |  |  | Manpower as per DPR
Priority | Project | SPV | Plot No | Category | Category | MMS Type | Module Source | Capacity (MWac) | OL | Capacity (MWdc) | PSS No. | PSS Charging Date | SCOD | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 |  | Charging | Trail Run | Trail Run Certificate | Piling | MMS (Purlin) | Module | IDT | Avaliable as of 27/28-Dec | Required
A. Khavda Solar Projects
1 | AGEL Merchant | ARE56L | S-08 | Merchant | Merchant | HSAT | ALMM | 250 | 1.37 | 342.5 | PSS-09 | 2024-11-16 |  |  | 75 | 50 |  | 125 | 0 | [7 empty] | 0 | 0 | 0 | Completed | Completed | Completed | Completed
2 | AGEL Merchant | ARE56L | A-02 | Merchant | Merchant | HSAT | ALMM | 50 | 1.37 | 68.5 | PSS-04 | 2025-02-26 |  |  | 50 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | Completed | Completed | Completed | Completed
3 | MLP AP New | ARE57L | A-11 | PPA | PPA | HSAT | China | 187.5 | 1.36 | 255 | PSS-13 | 2025-02-20 | 15-Jun-29 (LTA +15D) | 75 | 112.5 | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0 | Completed | Completed | Completed | Completed
4 | MLP AP New | ARE57L | A-12 | PPA | PPA | HSAT | China | 350 | 1.35 | 472.5 | PSS-13 | 2025-02-20 | 15-Jun-29 (LTA +15D) |  | 50 | 175 |  |  |  |  | 125 | [8 empty] | Completed | Completed | Completed | Completed | 0 | 0
5 | SECI H-3 | AHEJ5L | A-13 | PPA | PPA | FT | China | 570 | 1.4 | 798 | PSS-05 | 2025-03-05 | 31-Dec-25 (LTA) | 145 |  | 150 |  | 50 | 75 | 75 |  | 75 | [7 empty] | Completed | Completed | Completed | Completed | 7 | 7
6 | AGEL Merchant | ARE45L | A-14 | Merchant | Merchant | HSAT | ALMM | 250 | 1.37 | 342.5 | PSS-05 | 2025-03-05 |  | 50 |  | 125 |  |  | 75 | 0 | [9 empty] | Completed | Completed | Completed | Completed
7 | MLP T3 AP | ARE56L | S-06 | PPA | PPA | HSAT | China | 500 | 1.37 | 685 | PSS-10 | 2025-03-25 | 2025-11-29 | 100 |  | 137.5 |  | 87.5 | 100 |  | 75 | [8 empty] | Completed | Completed | Completed | Completed | 0 | 0
P-01 | Google Hybrid | ARE3L | A-6 | Merchant-Google | Merchant | HSAT | ALMM | 25 | 1.35 | 33.75 | PSS-08 | 2025-07-13 | - |  |  |  | 25 | 0 | 0 | 0 |  | 0 | [7 empty] | Completed | Completed | Completed | Completed
P-02 | AGEL Merchant | ASEJ6PL | A-6 | Merchant-Hybrid | Merchant | HSAT | ALMM | 35 | 1.35 | 47.25 | PSS-08 | 2025-07-13 | - |  |  |  | 35 | 0 | 0 | 0 |  | 0 | [7 empty] | Completed | Completed | Completed | Completed
P-03 | AGEL Hybrid Merchant | AGE25BL | S-8 | Merchant-Hybrid | Merchant | HSAT | ALMM | 100 | 1.35 | 135 | PSS-09 | 2024-11-16 | - | [5 empty] | 100 | [10 empty] | Completed | Completed | Completed | Completed
P-04 | AGEL Merchant | AHEJ5L | A-15a | Merchant | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 | PSS-08 | 2025-07-13 | - | [5 empty] | 50 |  |  |  | 50 | 50 | [5 empty] | 97% | 81.7% | 62% | C:92%; E:83% | 360 | 240
P-05 | AGEL Hybrid Merchant | AGE26BL | S-5 | Merchant-Hybrid | Merchant | HSAT | ALMM | 292 | 1.35 | 394.2 | PSS-10 | 2025-08-07 | - | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 50 | 50 | 75 | 67 | 0 | 0 |  |  | 0 | 99.4% | 89.6% | 58.4% | C:100%; E:83% | 358 | 480
P-05a | AGEL Hybrid Merchant | AGE26BL | S-5 | Merchant-Hybrid | Merchant | HSAT | ALMM | 142 | 1.35 | 191.7 |  | 2025-08-07 | - | [5 empty] | 50 |  | 50 |  |  | 42
P-05b | AGEL Merchant | AGE26BL | S-5 | Merchant-Hybrid | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 |  | 2025-08-07 | - | [8 empty] | 50 | 75 | 25
P-06 | AGEL Merchant | AGE24L | S-5 | Merchant | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 | PSS-10 | 2025-08-07 | - | [9 empty] | 62.5 | 87.5 | [5 empty] | 98% | 81.7% | 46.43% | C:100%; E:83% | 520 | 380
P-07 | AGEL Merchant | AGE24L | A-14 | Merchant | Merchant | HSAT | ALMM | 150 | 1.35 | 202.5 | PSS-05 | 2025-03-05 | - | [9 empty] | 75 | 75 | [5 empty] | 95% | 48.7% | 13.3% | C:50%; E:50% | 412 | 840
P-08 | Cement - Hybrid | ACL | A-1 | Cement - Hybrid | Group | FT | ALMM | 125 | 1.36 | 170 | PSS-04 | 2025-02-26 | - | [5 empty] | 50 |  |  | 75 | [7 empty] | Completed | Completed | Completed | Completed
P-09 | MLP T3 AP | AGE25CL | A-6 | PPA | PPA | HSAT | China | 75 | 1.35 | 101.25 | PSS-08 | 2025-07-13 | 2025-11-29 | [8 empty] | 75 |  |  | 0 |  |  |  |  | Completed | Completed | Completed | Completed
P-10 | MLP T1 J&K | AGE26AL | A-16a | PPA | PPA | FT | SEA | 50 | 1.3306 | 66.53 | PSS-06 | 2025-12-06 | 2026-01-12 | [9 empty] | 50 | [6 empty] | Completed | Completed | Completed | Completed | 129 | 250
P-11 | MLP T1 CG | AGE26AL | A-16b | PPA | PPA | FT | SEA | 200 | 1.3181 | 263.62 | PSS-06 | 2025-12-06 | 2026-01-12 | [9 empty] | 175 | 25 | [5 empty] | 77% | 41.7% | 27.8% | C:63%; E:63% | 659 | 1050
P-12 | MLP T1 TN | AGE26AL | A-16c | PPA | PPA | FT | SEA | 167 | 1.3293 | 222 | PSS-06 | 2025-12-06 | 2026-01-12 | [9 empty] | 100 | 67 | [5 empty] | 60.93% | 1.926% |  | C:0%; E:0% | 331 | 1020
P-13 | MLP T1 OR | AGE26AL | A-16d | PPA | PPA | FT | SEA | 333 | 1.3243 | 441 | PSS-06 | 2026-01-27 | 2026-01-12 | [9 empty] | 150 | 183 |  |  | 0 | 0 | 0 | 52.39% | 3% |  | C:15%; E:11% | 304 | 1620
P-14 | MLP T1 TR | AGE26AL | A10a | PPA | PPA | FT | SEA | 50 | 1.36 | 68 | PSS-03 | 2024-03-22 | 08-Dec-25 (LTA -23D) | [6 empty] | 50 | [6 empty] | 0 | 0 |  | 99.52% | 96.2% | 91% | Completed | 56 | 90
P-15 | MLP T3 AP | AGE25CL | A-6 | PPA | PPA | FT | China | 425 | 1.36 | 578 | PSS-08 | 2025-10-31 | 2025-11-29 | [9 empty] | 100 | 150 | 175 |  | 0 | 0 | 0 | 67.8% | 18.13% |  | C:59%; E:47% | 794 | 1420
| Subtotal (A) | [6 empty] | 4484.5 |  | 6092.1 |  |  |  | 370 | 287.5 | 637.5 | 60 | 262.5 | 500 | 125 | 250 | 275 | 837.5 | 704.5 | 175 |  | 0 | 0 | 0 |  |  |  |  | 3930 | 7397
D1. Khavda Solar (Copper + Merchant - 50 MW)
P-18a | KCTL | KCTL | A-15a | Group | Group | HSAT | ALMM | 12.5 | 1.35 | 16.875 | PSS-08 | 2025-10-31 | - | [10 empty] | 12.5 |  |  | 0 | 0 | 0 | [5 empty] | 30
P-18b | MCIPL | MCIPL | A-15a | Group | Group | HSAT | ALMM | 12.5 | 1.35 | 16.875 | PSS-08 | 2025-10-31 | - | [10 empty] | 12.5 |  |  | 0 | 0 | 0 | [5 empty] | 30
P-19 | AGEL Merchant | ASEJo6PL | A-15a | Merchant | Merchant | HSAT | ALMM | 25 | 1.35 | 33.75 | PSS-08 | 2025-10-31 | - | [10 empty] | 25 |  |  | 0 | 0 | 0 | [5 empty] | 60
| Subtotal (D1) | [6 empty] | 50 |  | 67.5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 | 0 | 0 | [5 empty] | 120
D2. Khavda Solar (Additional from Internal - 650 MW)
P-16 | AGEL Hybrid Merchant | AHEJ5L | S-4 | Merchant | Merchant | HSAT | ALMM | 300 | 1.35 | 405 | PSS-11 | 2025-12-05 | - | [13 empty] | 0 | 0 | 0 | [5 empty] | 890
P-17 | MLP AP New | ARE57L | A-12 | PPA | PPA | HSAT | China | 350 | 1.35 | 472.5 | PSS-13 | 2025-02-20 | 15-Jun-29 (LTA +15D) | [13 empty] | 0 | 0 | 0 | 98.61% | 1.87% | 0% | C:60%; E:7% |  | 870
| Subtotal (D2) | [6 empty] | 650 |  | 877.5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  |  |  |  | 0 | 1760
Overall Total (A + D1 + D2) | [7 empty] | 5184.5 |  | 7037.1 |  |  |  | 370 | 287.5 | 637.5 | 60 | 262.5 | 500 | 125 | 250 | 275 | 837.5 | 754.5 | 175 |  | 0 | 0 | 0 |  |  |  |  | 3930 | 9277
[11 empty] | PSS-03 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
[11 empty] | PSS-04 |  |  | 0 | 50 | 0 | 0 | 0 | 50 | 0 | 0 | 75 | 0 | 0 | 0
[11 empty] | PSS-05 |  |  | 195 | 0 | 275 | 0 | 50 | 150 | 75 | 0 | 75 | 75 | 75 | 0
[11 empty] | PSS-06 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 275 | 0
[11 empty] | PSS-08 |  |  | 0 | 0 | 0 | 60 | 0 | 50 | 0 | 0 | 75 | 150 | 250 | 175
[11 empty] | PSS-09 |  |  | 0 | 75 | 50 | 0 | 125 | 100 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | PSS-10 |  |  | 100 | 0 | 137.5 | 0 | 87.5 | 150 | 0 | 125 | 50 | 137.5 | 154.5 | 0
[11 empty] | PSS-11 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[11 empty] | PSS-13 |  |  | 75 | 162.5 | 175 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0
2642.5

## RJ Solar Plan (hidden)
FY 2025-26 ¦ RJ & AP Solar Projects Monthly Commissioning Plan (MWac) | [18 empty] | For Internal Purpose |  |  |  |  | Date: 1-Oct-25
Priority | Project | SPV | Location | Category | MMS Type | Capacity (MWac) | OL | Capacity (MWdc) | SCOD | Commissioning as per Business Plan | Capex BOQ Release Date | Till Feb-25 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Capex NFA Status
1 | Ambuja Cement Limited | ACL | Essel Park | Group | FT | 300 | 1.42 | 426 | NA | 2025-06-30 |  |  | 2025-06-01: 300
2 | Ultratech | ASEJ6PL | Bap | Merchant | HSAT | 50 | 1.37 | 68.5 | NA | 2025-06-30 |  |  | 2025-06-01: 50
3 | NHPC BOO | ASEB1PL | Baiya | PPA | FT | 600 | 1.36 | 816 | Extension awaited | 2026-02-28 | Capex Approved | [14 empty] | Approved
4 | MLP AP NEW | AGE26BL | Bandha | PPA | HSAT | 534 | 1.37 | 731.58 | 2026-10-01 | 2025-09-30 | Capex Approved |  | 2025-11-01: 250; 2025-12-01: 284 | Approved
5 | MLP T1 | AGE27L | Bandha | PPA | FT | 500 | 1.39 | 695 | LTA+60 Days | 2026-02-28 | 2024-11-12 |  | 2025-12-01: 200; 2026-01-01: 300
Total | [5 empty] | 1984 |  | 2737.08 |  |  |  | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 250 | 484 | 300 | 0 | 0 | #REF!
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.373

## RJ Solar Rephase (hidden)
FY 2025-26 ¦ RJ & AP Solar Projects Monthly Commissioning Plan (MWac) | [18 empty] | For Internal Purpose |  |  |  |  | Date: 1-Oct-25
Priority | Project | SPV | Location | Category | MMS Type | Capacity (MWac) | OL | Capacity (MWdc) | SCOD | Commissioning as per Business Plan | Capex BOQ Release Date | Till Feb-25 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Capex NFA Status
1 | Ambuja Cement Limited | ACL | Essel Park | Group | FT | 300 | 1.42 | 426 | NA | 2025-06-30 |  |  | 2025-07-01: 150; 2025-08-01: 150
2 | Ultratech | ASEJ6PL | Bap | Merchant | HSAT | 50 | 1.37 | 68.5 | NA | 2025-06-30 |  |  | 2025-06-01: 50
3 | NHPC BOO | ASEB1PL | Baiya | PPA | FT | 600 | 1.36 | 816 | Extension awaited | 2026-02-28 | Capex Approved | [14 empty] | Approved
4 | MLP AP NEW | AGE26BL | Bandha | PPA | HSAT | 534 | 1.37 | 731.58 | 2026-10-01 | 2025-09-30 | Capex Approved |  | 2025-12-01: 534 | Approved
5 | MLP T1 | AGE27L | Bandha | PPA | FT | 500 | 1.39 | 695 | LTA+60 Days | 2026-02-28 | 2024-11-12 |  | 2026-01-01: 250; 2026-02-01: 250
Total | [5 empty] | 1984 |  | 2737.08 |  |  |  | 0 | 0 | 0 | 0 | 50 | 150 | 150 | 0 | 0 | 0 | 534 | 250 | 250 | 0 | #REF!
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.373

## RJ Solar - Actual
FY 2025-26 ¦ RJ & AP Solar Projects Monthly Commissioning Plan (MWac) | [23 empty] | Date: 26-Dec-25
Priority | Project | SPV | Location | Category | MMS Type | Capacity (MWac) | OL | Capacity (MWdc) | SCOD | Commissioning as per Business Plan | Capex BOQ Release Date | Till Feb-25 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
1 | Ambuja Cement Limited | ACL | Essel Park | Group | FT | 300 | 1.42 | 426 | NA | 2025-06-30 |  |  | 2025-08-01: 150; 2025-12-01: 150
2 | Ultratech | ASEJ6PL | Bap | Merchant | HSAT | 50 | 1.37 | 68.5 | NA | 2025-06-30 |  |  | 2025-06-01: 50
3 | NHPC BOO | ASEB1PL | Baiya | PPA | FT | 600 | 1.36 | 816 | Extension awaited | 2026-02-28 | Capex Approved |  | 2026-03-01: 300
4 | MLP AP NEW | AGE26BL | Bandha | PPA | HSAT | 534 | 1.37 | 731.58 | 2026-10-01 | 2025-09-30 | Capex Approved
5 | MLP T1 | AGE25BL | Bandha | PPA | FT | 500 | 1.39 | 695 | LTA+60 Days | 2026-02-28 | 2024-11-12 |  | 2026-03-01: 250 | 1034 | 484
Total | [5 empty] | 1984 |  | 2737.08 |  |  |  | 0 | 0 | 0 | 0 | 50 | 0 | 150 | 0 | 0 | 0 | 150 | 0 | 0 | 550
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1.373

## KH Wind Plan (hidden)
FY 2024-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) | [16 empty] | Date: 31-Mar-25
Sl. | Project | SPV | Category | Capacity (MW) | WTG Nos. | PSS No. | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
1 | AGEL Merchant (Wind) | AGE24L | Merchant | 52 | 10 | PSS-04 | 52
2 | Hybrid Cement (Wind) | ACL | Group | 57.2 | 11 | PSS-04 | 26 | 31.2
3 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 62.4 | 12 | PSS-04 | 52 | 10.4
4 | AGEL Hybrid Merchant (Wind) | AGE26BL | Merchant | 156 | 30 | PSS-10 | 52 | 104
5 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 67.6 | 13 | PSS-08 |  |  | 67.6
6 | AGEL Merchant (Wind) | ARE41L | Merchant | 130 | 25 | PSS-08 |  | 36.4 | 93.6
7 | Google Hybrid (Wind) | ARE3L | Merchant | 15.6 | 3 | PSS-08 |  |  | 15.6
8 | Google Hybrid (Wind) | ARE3L | Merchant | 26 | 5 | PSS-08 | 0 |  | 26
9 | AGEL Hybrid Merchant (Wind) | ASEJ6PL | Merchant | 62.4 | 12 | PSS-08 |  |  | 41.6 | 20.8
10 | SECI H-3 (Wind) | AHEJ5L | PPA | 202.8 | 39 | PSS-05 |  |  |  | 72.8 | 26 | 26 | 52 | 26
11a | AGEL Merchant (Wind) | AGE25CL | Merchant | 156 | 30 | PSS-11 | [7 empty] | 104 | 52
12a | AGEL Merchant (Wind) | AGE26AL | Merchant | 140.4 | 27 | PSS-12 | [8 empty] | 78 | 62.4
| Total |  |  | 1128.4 | 217 |  | 182 | 182 | 244.4 | 93.6 | 26 | 26 | 52 | 130 | 130 | 62.4 | 0 | 0
11b | AGEL Merchant (Wind) | AGE25CL | Merchant | 98.8 | 19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.8 | 0 | 0
[6 empty] | PSS-11 | [9 empty] | 31.2
[6 empty] | PSS-14 | [9 empty] | 67.6
12b | AGEL Merchant (Wind) | AGE26AL | Merchant | 312 | 60 | PSS-12 | [9 empty] | 41.6 | 156 | 114.4
13 | AGEL Merchant | AGE25BL | Merchant | 10.4 | 2 | PSS-09 | [8 empty] | 10.4
| Total (for Internal) |  |  | 421.2 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 140.4 | 156 | 114.4
| Total |  |  | 1549.6 | 298 | 0 | 182 | 182 | 244.4 | 93.6 | 26 | 26 | 52 | 130 | 140.4 | 202.8 | 156 | 114.4

## KH Wind Rephase (hidden)
FY 2024-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) | [8 empty] | Chairman Budget Purpose Revised | [7 empty] | Date: 30-Jun-25
Sl. | Project | SPV | Category | Capacity (MW) | WTG Nos. | PSS No. | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
1 | AGEL Merchant (Wind) | AGE24L | Merchant | 52 | 10 | PSS-04 | 52
2 | Hybrid Cement (Wind) | ACL | Group | 57.2 | 11 | PSS-04 |  | 26 | 31.2
3 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 62.4 | 12 | PSS-04 | 52 |  | 10.4
4 | AGEL Hybrid Merchant (Wind) | AGE26BL | Merchant | 156 | 30 | PSS-10 |  |  | 119.6 | 26 | 10.4
5 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 67.6 | 13 | PSS-08 | [5 empty] | 52 | 15.6
6 | AGEL Merchant (Wind) | ARE41L | Merchant | 130 | 25 | PSS-08 |  |  |  | 52 | 26 | 26 | 26
7 | Google Hybrid (Wind) | ARE3L | Merchant | 15.6 | 3 | PSS-08 |  |  |  |  | 15.6
8 | Google Hybrid (Wind) | ARE3L | Merchant | 26 | 5 | PSS-08 | 0 |  |  |  | 26
9 | AGEL Hybrid Merchant (Wind) | ASEJ6PL | Merchant | 62.4 | 12 | PSS-08 | [6 empty] | 62.4
10 | SECI H-3 (Wind) | AHEJ5L | PPA | 202.8 | 39 | PSS-05 | [7 empty] | 104 | 98.8
11a | AGEL Merchant (Wind) | AGE25CL | Merchant | 156 | 30 | PSS-11 | [9 empty] | 104 | 52
12a | AGEL Merchant (Wind) | AGE26AL | Merchant | 140.4 | 27 | PSS-12 | [10 empty] | 78 | 62.4
| Total |  |  | 1128.4 | 217 |  | 104 | 26 | 161.2 | 78 | 78 | 78 | 104 | 104 | 98.8 | 104 | 130 | 62.4
11b | AGEL Merchant (Wind) | AGE25CL | Merchant | 98.8 | 19 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98.8 | 0 | 0
[6 empty] | PSS-11 | [9 empty] | 31.2
[6 empty] | PSS-14 | [9 empty] | 67.6
12b | AGEL Merchant (Wind) | AGE26AL | Merchant | 312 | 60 | PSS-12 | [9 empty] | 41.6 | 156 | 114.4
13 | AGEL Merchant | AGE25BL | Merchant | 10.4 | 2 | PSS-09 | [8 empty] | 10.4
| Total (for Internal) |  |  | 421.2 | 81 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4 | 140.4 | 156 | 114.4
| Total |  |  | 1549.6 | 298 | 0 | 104 | 26 | 161.2 | 78 | 78 | 78 | 104 | 104 | 109.2 | 244.4 | 286 | 176.8

## KH Wind Internal
FY 2025-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) (Phase-02 Carry forward) | [13 empty] | For Internal Purpose | [6 empty] | Date : 08-Dec-25
Sl. | Project | SPV | Category | Total Capacity (MW) | Total WTG Nos. | PSS No. | PSS Charging Date | Till Mar-25 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY 25-26 Total (Plan) |  | FY 25-26 Commissioned till Nov-25 |  | FY 24-25 Commissioned |  | Total Commissioned till Nov-25
[21 empty] | WTG | MW | WTG | MW | WTG | MW | WTG | MW
1 | Hybrid Port (Wind) | APSEZ | Group | 20.8 | 4 | PSS-3 | Charged | 20.8 | [12 empty] | 0 | 0 | 0 | 0 | 4 | 20.8 | 4 | 20.8 |  | 0
2 | AGEL Merchant (Wind) | ARE41L | Merchant | 260 | 50 | PSS-3 | Charged | 260 | [12 empty] | 0 | 0 | 0 | 0 | 50 | 260 | 50 | 260 |  | 0
3 | AGEL Hybrid Merchant (Wind) | ARE48L AGE25BL | Merchant | 119.6 | 23 | PSS-09 | Charged | 119.6 | [12 empty] | 0 | 0 | 0 | 0 | 23 | 119.6 | 23 | 119.6 |  | 0 | 5229
4 | AGEL Merchant (Wind) | ARE41L | Merchant | 124.8 | 24 | PSS-13 | Charged | 124.8 | [12 empty] | 0 | 0 | 0 | 0 | 24 | 124.8 | 24 | 124.8 |  | 0
5 | AGEL Merchant (Wind) | AGE24L | Merchant | 104 | 20 | PSS-04 | Charged | 52 | 2025-04-01: 52 | 10 | 52 | 10 | 52 | 10 | 52 | 20 | 104 |  | 0 | 4
6 | Hybrid Cement (Wind) | ACL | Group | 156 | 30 | PSS-04 | Charged | 98.8 | 2025-05-01: 26; 2025-06-01: 31.2 | 11 | 57.2 | 11 | 57.2 | 19 | 98.8 | 30 | 156 |  | 0
7 | Hybrid Port (Wind) | APSEZ | Group | 52 | 10 | PSS-04 | Charged | 52 | [12 empty] | 0 | 0 | 0 | 0 | 10 | 52 | 10 | 52 |  | 0
8 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 62.4 | 12 | PSS-04 | Charged |  | 2025-04-01: 52; 2025-06-01: 10.4 | 12 | 62.4 | 12 | 62.4 | 0 |  | 12 | 62.4 |  | 0 | 2.4
9 | AESL PPA (C&I) - Wind - RSWM | ARE41L | Merchant | 52 | 10 | PSS-04 | Charged | 52 | [12 empty] | 0 | 0 | 0 | 0 | 10 | 52 | 10 | 52 |  | 0
10 | AGEL Hybrid Merchant (Wind) | AGE26BL | Merchant | 156 | 30 | PSS-10 | Charged |  | 2025-06-01: 119.6; 2025-07-01: 26; 2026-03-01: 10.4 | 30 | 156 | 28 | 145.6 | 0 |  | 28 | 145.6 |  | 0
11 | AGEL Merchant (Wind) | AHEJ5L | Merchant | 67.6 | 13 | PSS-08 | Charged |  | 2025-09-01: 31.2; 2025-11-01: 31.2; 2026-01-01: 5.2 | 13 | 67.6 | 12 | 62.4 | 0 |  | 12 | 62.4 |  | 0 |  | SPV | PSS | WTGs | MW
12 | AGEL Merchant (Wind) | ARE41L | Merchant | 130 | 25 | PSS-08 | Charged |  | 2025-08-01: 124.8; 2025-11-01: 5.2 | 25 | 130 | 25 | 130 | 0 |  | 25 | 130 |  | 0 |  | AHEJ5L | PSS-08 | 7 | 36.4
13 | Google Hybrid (Wind) | ARE3L | Merchant | 15.6 | 3 | PSS-08 | Charged |  | 2025-07-01: 15.6 | 3 | 15.6 | 3 | 15.6 | 0 |  | 3 | 15.6 |  | 0 |  | ARE41L | PSS-08 | 1 | 5.2
Monthwise FY 24-25 Projects (A) - Total (MW) |  |  |  | 1320.8 |  |  |  | 780 | 104 | 26 | 161.2 | 41.6 | 124.8 | 31.2 | 0 | 36.4 | 0 | 5.2 | 0 | 10.4 | 104 | 540.8 | 101 | 525.2 | 150 | 780 | 251 | 1305.2 |  |  |  | ASEJ6PL | PSS-08 | 10 | 52
Total (No of WTG's) |  |  |  |  | 254 |  |  | 150 | 20 | 5 | 31 | 8 | 24 | 6 | 0 | 7 | 0 | 1 | 0 | 2 | [11 empty] | AHEJ5L (PPA) | PSS-05 | 18 | 93.6
[32 empty] | Total |  | 36 | 187.2
[7 empty] | Category | Till Dec-24 |  |  |  | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[7 empty] | Merchant | 608.4 |  |  |  | 41.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4
[7 empty] | PPA | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Group | 171.6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | EPC | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Total | 780 |  |  |  | 41.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.4
96
FY 2025-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac) (Phase-03)
Sl. | Project | SPV | Category | Total Capacity (MW) | Total WTG Nos. | PSS No. | PSS Charging Date | Till Mar-25 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY 25-26 Total (Plan) |  | FY 25-26 Commissioned till Nov-25 |  | FY 24-25 Commissioned |  | Total Commissioned till Nov-25
[21 empty] | WTG | MW | WTG | MW | WTG | MW | WTG | MW
1 | Google Hybrid (Wind) | ARE3L | Merchant | 26 | 5 | PSS-08 | Charged |  | 2025-07-01: 26; 2025-12-01: nnd--2 | 5 | 26 | 5 | 26 | NA | NA | 5 | 26 | 22.8846 | 17.8846
2 | AGEL Hybrid Merchant (Wind) | ASEJ6PL | Merchant | 62.4 | 12 | PSS-08 | Charged |  | 2025-12-01: 20.8; 2026-01-01: 15.6; 2026-02-01: 26 | 12 | 62.4 | 0 | 0 | NA | NA | 0 | 0 | 26.3077 | 14.3077
3 | AGEL Merchant (Wind) | AGE25BL | Merchant | 10.4 | 2 | PSS-09 | Charged |  | 2025-12-01: 5.2; 2026-01-01: 5.2 | 2 | 10.4 | 0 | 0 | NA | NA | 0 | 0 | 4.3846 | 2.3846
4 | SECI H-3 (Wind) | AHEJ5L | PPA | 202.8 | 39 | PSS-05 | Charged |  | 2025-10-01: 78; 2025-11-01: 83.2; 2025-12-01: 20.8; 2026-03-01: 20.8 | 39 | 202.8 | 31 | 161.2 | NA | NA | 31 | 161.2 | 159.4231 | 120.4231
5 | AGEL Merchant (Wind) | AGE25CL | Merchant | 187.2 | 36 | PSS-11 | 2025-08-31 |  | 2025-12-01: 104; 2026-01-01: 78; 2026-02-01: 5.2 | 36 | 187.2 | 0 | 0 | NA | NA | 0 | 0 | 78.9231 | 42.9231
6 | AGEL Merchant (Wind) | AGE26AL | Merchant | 140.4 | 27 | PSS-12 | 2025-08-31 |  | 2026-01-01: 98.8; 2026-02-01: 41.6 | 27 | 140.4 | 0 | 0 | NA | NA | 0 | 0 | 59.1923 | 32.1923
8 | AGEL Merchant (Wind) | AGE25CL | Merchant | 67.6 | 13 | PSS-14 | 2025-11-30 |  | 2026-02-01: 26; 2026-03-01: 41.6 | 13 | 67.6 | 0 | 0 | NA | NA | 0 | 0 | 28.5 | 15.5
9 | AGEL Merchant (Wind) | AGE26AL | Merchant | 312 | 60 | PSS-14 | 2025-11-30 |  | 2026-01-01: 20.8; 2026-02-01: 124.8; 2026-03-01: 166.4 | 60 | 312 | 0 | 0 | NA | NA | 0 | 0 | 131.5385 | 71.5385
Monthwise FY 25-26 Projects (B) - Total (MW) |  |  |  | 1008.8 |  |  |  | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 78 | 83.2 | 150.8 | 218.4 | 223.6 | 228.8 | 194 | 1008.8 | 36 | 187.2 | NA | NA | 36 | 187.2
Monthwise FY 25-26 Projects (B) - Total (WTGs) |  |  |  |  | 194 |  |  | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 15 | 16 | 29 | 42 | 43 | 44
Monthwise FY 24-26 Projects (A+B) - Total (MW) |  |  |  | 2329.6 |  |  |  | 780 | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 119.6 | 150.8 | 223.6 | 223.6 | 239.2 | 298 | 1549.6 | 137 | 712.4 | 150 | 780 | 287 | 1492.4
[9 empty] | 2025-04-01: 291.2; 2025-07-01: 223.6; 2025-10-01: 348.4; 2026-01-01: 686.4 | 0
Monthwise FY 24-26 Projects (A+B) - Total (WTGs) |  |  |  |  | 448 |  |  | 150 | 20 | 5 | 31 | 13 | 24 | 6 | 15 | 23 | 29 | 43 | 43 | 46
[7 empty] | 0 |  | 2025-04-01: 56; 2025-07-01: 43; 2025-10-01: 67; 2026-01-01: 132
Note : WTG Commissioning of PSS-11 & 12 is linked with PSS charging.
[7 empty] | PSS Charging Date | Till Mar-25 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | FY 25-26 Total (Plan) |  | FY 25-26 Commissioned till Nov-25 |  | FY 24-25 Commissioned |  | Total Commissioned till Nov-25
[21 empty] | WTG | MW | WTG | MW | WTG | MW | WTG | MW
| Overall Status | WTG | MW |  |  | PPA | PPA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 83.2 | 20.8 | 0 | 0 | 20.8 | 39 | 202.8 | 31 | 161.2 | 0 | 0 | 31 | 161.2
| Total Plan | 448 | 2329.6 |  |  | Merchant | Merchant | 608.4 | 104 | 0 | 130 | 67.6 | 124.8 | 31.2 | 0 | 36.4 | 130 | 223.6 | 223.6 | 218.4 | 248 | 1289.6 | 95 | 494 | 117 | 608.4 | 212 | 1102.4
| Total Actual | 287 | 1492.4 |  |  | Group | Group | 171.6 | 0 | 26 | 31.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 57.2 | 11 | 57.2 | 33 | 171.6 | 44 | 228.8
[7 empty] | Total | 780 | 104 | 26 | 161.2 | 67.6 | 124.8 | 31.2 | 78 | 119.6 | 150.8 | 223.6 | 223.6 | 239.2 | 298 | 1549.6 | 137 | 712.4 | 150 | 780 | 287 | 1492.4
FY 2024-26 ¦ Khavda Wind Projects Monthly Commissioning Plan (MWac)
[7 empty] | Category | Till Dec-24 | 2025-04-01: 2025-04-01; 2025-05-01: 2025-05-01; 2026-01-01: 2026-01-01; 2026-02-01: 2026-02-01; 2026-03-01: 2026-03-01
[7 empty] | Merchant | 1216.8 | 2025-04-01: 104; 2025-05-01: 0; 2026-01-01: 223.6; 2026-02-01: 223.6; 2026-03-01: 228.8
[7 empty] | PPA | 0 | 2025-04-01: 0; 2025-05-01: 0; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 20.8
[7 empty] | Group | 343.2 | 2025-04-01: 0; 2025-05-01: 26; 2026-01-01: 0; 2026-02-01: 0; 2026-03-01: 0
[7 empty] | EPC | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[7 empty] | Total | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[8 empty] | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[9 empty] | #REF! | [9 empty] | #REF!
[8 empty] | #REF! | 2025-04-01: #REF!; 2025-05-01: #REF!; 2026-01-01: #REF!; 2026-02-01: #REF!; 2026-03-01: #REF!
[9 empty] | #REF! | [9 empty] | #REF!
[9 empty] | 0 | 0 | [7 empty] | 42 | 43 | 44
[9 empty] | 104 | 26 | [7 empty] | 223.6 | 223.6 | 239.2

## Wind Mundra (hidden)
FY 2025-26 ¦ Wind Projects (O/S Khavda Monthly Commissioning Plan (MWac) | [16 empty] | Date: 1-Oct-25
Priority | Project | SPV | Location | Category | Category | Capacity (MW) | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
P-01 | AGEL Merchant (Wind) | AGE32L | Mandvi | Merchant-Wind | Merchant | 260.7
P-02 | AGEL Merchant (Wind) | AWEK3L | Mundra North | Merchant-Wind | Merchant | 323.4 | 2026-03-01: 198
Total | [5 empty] | 584.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198
[7 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0